## Onboarding and Offboarding plan
Onboarding and Offboarding plan
Project: | Daimler-VBTO | Name of the Team Member: | Abhishek Kumar | Manager | Anushree Jamsandekar
Project Id: | 100398922 | Employee Id: | 143902 | Base Location | Mumbai
Date of On board: | 2019-01-08 | Date of Off board:
Topic | Task | Task Details | Person Responsible/KT Provider | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Status
Standard On boarding Process Activities
Standard | Create User ID, mail id and Discover training |  | HR / ITICS |  |  |  |  | Closed
Project Specific On boarding Process Activities
Introduction | Introduction to the team Buddy allocation | Introduction to the team Buddy allocation | PM | 2019-01-08 | 2019-01-08 | 2019-01-08 | 2019-01-08 | Closed
Project Overview | a. Brief overview of Account b. Project Overview and life cycle c. Org Structure for both offsite and onshore teams d. Roles and responsibilities | a. Brief overview of Account b. Project Overview and life cycle c. Org Structure for both offsite and onshore teams d. Roles and responsibilities | PM / Buddy (Abhay) | 2019-01-14 | 14-01-2019 | 2019-01-15 | 2019-01-15 | Closed
Workstation | Desktop/Laptop/Desk allocation | Desktop/Laptop/Desk allocation | PM / PMO | 2019-01-09 | 2019-01-09 | 2019-01-11 | 2019-01-17 | Closed
Access | Access to environments, servers, project wiki and tools: SVN, PE, Confluence, JIRA, Troom | Access to environments, servers, project wiki and tools: SVN, PE, Confluence, JIRA, TeamForge | Xtech / CM / PQL | 2019-01-14 | 2019-01-14 | 2019-01-10 | 2019-01-14 | Closed
Functional | Project Overview a. Background b. Requirements Overview c. Application Overview | End to end functional overview (process flow) of import, statistical analysis, post-processing, buildability check, configuration editing and ordering. | Arati | 2019-01-21 | 2019-01-21 |  |  | New
Functional | Requirement / Business Process a. BRD b. SRS | Overview of the specification process, structure of the BRD and SRS documents. | Arati | 2019-01-21 | 2019-01-21 |  |  | New
Functional | Application Walkthrough a. UI Walkthrough b. User Authentication and Data Authorizations, Roles c. Administration | Application demo of all the screens for different user roles. | Arati | 2019-01-22 | 2019-01-22 |  |  | New
Technical | Database overview - IBM DB2 | Overview of DB2 database and data model at high level. | Prathamesh Prabhu | 2019-01-23 | 2019-01-23 |  |  | New
Technical | Overview of Data Model a. Statistical Run Management b. Configuration Management c. Master Data Management | Overview of database tables associated with each of these modules and information stored in each of the tables. | Prathamesh Prabhu | 2019-01-24 | 2019-01-24 |  |  | New
Technical | Architecture Overview: a. Application Architecture b. System Architecture | Overview of technology stack, IDE, servers, frameworks used in the project. Detailed overview of system architecture and application architecture. | Praveen Ramrakhiyani | 2019-01-25 | 2019-01-25 |  |  | New
Technical | Code walkthrough a. Dialog a. Interface | Code walkthrough of application, classes module-wise for all the different dialogs and interfaces. | Abhay | 2019-01-28 | 2019-01-28 |  |  | New
Technical | Overview testing tools a. Junit | How is Junit used in the project as a testing tool? How to create and execute Junit test cases for business logic. | Vandita | 2019-01-29 | 2019-01-29 |  |  | New
Tool Training | Overview of technical tools a. Eclipse and plugins b. SVN c. DB Visualiser d. WAS e. Maven | a. Overview of Eclipse IDE for coding, committing the code in SVN, workspace steup. B. SVN repository structure, code locations and how to use SVN in general. C. Overview of DBVisualiser tool, how to connect to database and run queries. d. Setup of WAS, how to instal the project EAR file and how to work with WAS. e. How to build the EAR using Maven, overview of Maven. | Shashank Singh | 2019-01-29 | 2019-01-29 |  |  | New
Tool Training | Overview of other tools a. Project Environment b. Confluence c. JIRA d. TeamForge | a. Overview of VBtO PE. B. Overview of confluence tool and information contained in it like release overview, How to articles, technical details for different environments etc. C. Overview of Jira as to how to create and track issues. Overview of how PMF is implemented using Jira, how to log effort in Jira. d. Overview of TeamForge and document structure. | Shashank Singh | 2019-01-29 | 2019-01-29 |  |  | New
Processes | Overview of Processes a. Development process b. Specification process c. Bug fixing process d. Testing process e. Quality process f. Build process g. Release process | a. Overview of development process - ITC writing, coding and unit testing process. B. Specification process in terms of BRD and SRS. C. Bug fixing process for unit testing, module testing, integration testing and UAT. d. Overview of what are the different kinds of testing done in the project in different phases. | Benugopal | 2019-01-30 | 2019-01-30 |  |  | New
Operational | Operational Topics a. Project dashboard b. Usage of SVN c. RACI d. Vacation plan e. Time Card/Clarity f. PMD | a. Overview of dStum board, dBrief board and other dashboards used in the project. B. How to add/modify/delete files in SVN C. Location and overview of RACI matrix, team calander(vacation plans). E. How to fill Jira, India time card and clarity on a weekly basis. F. Overview of the PMD process. | Benugopal | 2019-01-31 | 2019-01-31 |  |  | New
Assignment | Assignment in JSF, EJB and JPA
Standard Off boarding Process Activities
Standard | All open tasks and reviews are closed in tools like clarity, Timesheets etc |  | PM | N/A
Access | Access has been disabled for servers, network access and tools |  | Xtech / CM / PQL | N/A
Handover | Surrender / Transfer of Desktop/laptop |  | PM / PMO | N/A
Handover | Surrender / Transfer of Secure ID / Safeword Token |  | PM / PMO | N/A
Project Specific Off boarding Process Activities
Please list down the specific topics here e.g. KT of bug fixing, CR/SRS etc.
Prepare KT document and provide to the recipient |  |  | KT Provider | N/A
Signoff from both KT provider and Recipient |  |  | KT Receiver | N/A
Note on A5: To be updated when project code is changed
Note on A6: It is the date on which the new resource joined the project
Note on C6: It is the date on which the resource leave the project
Note on D8: Put responsible name against each task wherever applicable
Note on B10: Applicable only if new to organization else set NA